## Project Planner
Project Plan - Gantt Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 24 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START (Week) | PLAN DURATION (Weeks) | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Weeks (Commencing UNI Week 7 - 13/11/2017) | [22 empty] | HAND IN WEEK
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Maze Generation Research | 1 | 2 | 0 | 2 | 100%
Maze Generation | 2 | 2 | 2 | 2 | 100%
Maze Graphical Design | 2 | 2 | 2 | 1 | 100%
Complete Game | 4 | 20 | 1 | 23 | 100%
Player Character creation and Basic Abilities (movement,health) | 4 | 1 | 3 | 4 | 100%
Enemies (basics) | 5 | 1 | 3 | 3 | 100%
Enemies (Ongoing AI tweaks, improvements and enemy addiitons) | 6 | 18 | 6 | 18 | 100%
Player Escape Run back through maze/s | 6 | 2 | 10 | 1 | 100%
Add Collectable Treasure That spawns in maze appropriatly | 8 | 2 | 10 | 1 | 100%
Sight and torch Mechanic | 9 | 2 | 4 | 1 | 100%
Upgrades That can be bought with collected treasure( after some of the other stuff cause need those implemented to be upgraded) | 10 | 2 | 9 | 2 | 100%
Game Mechanic Changing Items | 10 | 4 | 11 | 3 | 100%
Getting Items To spawn in maze appropriatly | 10 | 4 | 11 | 3 | 100%
Sub-Boss Minotaur | 14 | 2 | 13 | 1 | 100%
Minimap | 16 | 3 | 14 | 2 | 100%
Improvements, Additions, and unlisted Mechanics | 19 | 5 | 1 | 23 | 100%
Traps |  |  | 20 | 1 | 100%
Menus and GUI |  |  | 9 | 10 | 100%
Save And Load Function |  |  | 22 | 1 | 100%
Textures and Sounds |  |  | 2 | 21 | 100%
Additional enemies |  |  | 3 | 10 | 100%
Testing | 1 | 23 | 1 | 23 | 100%